## Sheet1
File Number | 1/8/2024 Accela Status | 12/1/2023 Accela status | Parcel Number | KK Notes | Number of Unit(s) | RBU | Source of Unit | Deed Restriction in LT Info | Constructed | Open Date | Project Type | Applicant | Owner | Project Notes (short description) | Hard copy or Electronic H or E | Incomplete Email Sent Day Shortcut: ctrl ; | Incomplete Email Sent By | Day it became complete (if incomplete) | Assigned to | Notes | County | Status | Deed-Restricted or Market Rate | Recorded in "Large Project Tracking Spreadsheet?" | Time from Open to Conditional Permit - months | Time from Open to Conditional Permit - days (approximate) | Time from Conditional to Acknowledged Permit - days (approximate)
ERSP2022-1998 | Conditional Permit | Conditional Permit | 023-151-030 | Deed-restricted accessory dwelling unit (ADU) within an existing detached garage | 1 | Yes | TRPA-ALLOC-2329 | Not filed yet - achievable | Issued, Not acknowledged | 2022-11-18 | Residential Dwelling | MORS | MORS NATE & SIERRA |  | e-TLS | 44895 | TLS | 45118 | Jen |  | South Lake Tahoe | Conditional Permit 10/9/23 | DR
ERSP2023-0009 | Conditional Permit | Conditional Permit | 094-052-011 | New garage with ADU | 1 | Yes | TRPA-ALLOC-2328 | Not filed yet - achievable | Issued, Not acknowledged | 2023-01-06
ERSP2023-1200 | Conditional Permit | Conditional Permit | 094-122-023 | Detached 400 square foot deed-restricted accessory dwelling unit (ADU) and carport. Achievable Bonus Unit from TRPA pool | 1 | Yes | TRPA-ALLOC-2347 | Not filed yet - achievable | Issued, Not acknowledged | 2023-08-21
ERSP2022-1314 | Conditional Permit | Conditional Permit | 026 152 002 | Reconstruction of an existing illegal ADU, The project will receive a Bonus Unit from the “TRPA Bonus Unit Pool – Affordable” with deed restriction | 1 | Yes | TBD | TBD - Affordable | Issued, Not acknowledged | 2022-07-06 | Residential Dwelling | Davidson | DAVIDSON ANNE H | Residence B @ 2890 Sacramento Ave in South Lake Tahoe, CA (parcel 026 152 002) to become an ADU as-is |  |  |  |  | Alyssa Bettinger |  | South Lake Tahoe | Conditional Permit 9/9/2022 | DR |  | 2 | 63
ERSP2019-1196 | Acknowledged | Acknowledged | 094-070-006 | Caretakers housing unit that is an accessory | 1 | Yes | TRPA-ALLOC-1329 | Yes - Achievable | Acknowledged, Not Completed | 2019-09-10 | Achievable Moderate Income bonus unit on commercial property. Mixed-use Permit issued based on new plans dated 11.20.20 |  | Samir Tuma | Add caretaker unit to commercial property |  |  |  |  | Paul Nielsen | Acknowledged Sept. 2021 | Placer | Acknowledged 9/14/2021 Conditional Permit 12/21/2020 | DR | Yes | 15.5 | 465 | Talked to Samir on 2/1/2023 and he said the unit should be done in about four months (April 2023)
ERSP2020-1952 | Project Complete | Project Complete | 097-161-004 | Convert existing cabin into ADU | 1 | Yes | TRPA-ALLOC-1721 | Yes - Achievable | Completed | 2020-11-02 | Residential Dwelling | Edward Kriston Construction | David and Florence Stronck | Convert existing cabin into ADU | H |  |  | 44351 | Karen |  | Placer | Complete - 9/2/2022 Conditional Permit 9/4/2021 | DR | Yes | 10 | 300 | Total
ERSP2021-0366 | Conditional Permit | Conditional Permit | 111-100-028 | New detached garage with accessory living space above. | 1 | Yes | TRPA-ALLOC-1888 | Yes - Achievable | Issued, Not acknowledged | 2021-04-08 | Residential Dwelling | Anderson | CERUTI | New detached garage with ADU above. | E | 4/15 to kba@ltvista.com | Robbie |  | Theresa | Applicant is Anderson | Placer | Conditional 7/8/2022 | DR |  | 15 | 450 |  | 1 | Conditional Permit
ERSP2021-1742 | Project Complete | Project Complete | 094-213-003 | Convert storage to an ADU | 1 | Yes | TRPA-ALLOC-1884 | Yes - Achievable | Completed | 2021-11-29 | Residential Dwelling | Gemme | Granlibakken | Convert what was permitted with PCBD as storage to an ADU with full bathroom and full kitchen. PCBD deferred to TRPA as PCBD was unsure of TRPA's stance on the Full Kitchen and Full Bathroom ADU. Structure is built just looking to convert the lower floor to living from originally permitted storage. |  |  |  |  | Theresa |  | Placer | Complete-10/20/22 Acknowledged-10/20/22 Conditional Permit - 3/21/22 | DR |  | 4.5 | 135 | Talked to Theresa 8/25/22, he wants to go with Achievable even though mostly wants to use it as guest house for kids. That's ok. She's issuing deed-restriction today.
ERSP2021-1944 | Acknowledged | Acknowledged | 116-050-020 | Detached Garage with 532sq ft ADU above | 1 | Yes | TRPA-ALLOC-1860 | Yes - Achievable | Acknowledged, Not Completed | 2021-12-15 | Residential Dwelling | Brown |  | Detached Garage with 532sq ft ADU above. Already permitted by Placer? | E |  |  | 44574 | Brandy |  | Placer | Acknowledged 7/12/2022 Conditional Permit 1/13/2022 | DR |  | 1 | 28
ERSP2022-0257 | Project Complete | Project Complete | 026-094-026 | Storage space converted into living space | 1 | Yes | TRPA-ALLOC-1887 | Yes - Achievable | Completed | 2022-03-04 | Residential Dwelling |  | Honorof | Convert living space into Deed-restricted ADU |  |  |  |  | Karen |  | City of South Lake Tahoe | Complete - 7/19/2022 Conditional Permit 3/19/2022 | DR |  | 0.5 | 15
ERSP2022-1407 | Acknowledged | Acknowledged | 031-172-011 | ADU above a garage | 1 | Yes | TRPA-ALLOC-2026 | Yes - Achievable | Acknowledged, Not Completed | 2022-07-20 | Residential Dwelling | Anna Russel | Lopes Hawley | 2721 Bertha |  |  |  |  | Karen |  | City of South Lake Tahoe | Acknowledged 10/5/2022 Conditional Permit 9/23/22 | DR |  | 2 | 63
ERSP2022-2016 | Acknowledged | Acknowledged | 117-100-088 | attached 2 car garage with ADU "bonus" unit above | 1 | Yes | TRPA-ALLOC-2144 | Yes - Achievable | Acknowledged, Not Completed | 2022-11-29 | Residential Dwelling | Janhunen | JANHUNEN WILLIAM | ADU: Existing 3 bed, 2 bath residence addition to include attached 2 car garage with ADU "bonus" unit above (1 bed, 1 bath) and new main floor aud/laundry and office Submitted to TRPA for Bonus Unit approval only, Placer county is conduction BMP and Coverage review. | e-TLS | 44909 | TLS | 44910 | Aly B. | ADU Bonus Unit Approval- confirmation of deed restriction email included in documents and Grant Deed has been uploaded | Placer County | Acknowledged 5/5/2023 Conditional Permit 3/17/2023 | DR |  | 3.5 | 105
ERSP2022-2018 | Acknowledged | Acknowledged | 023-655-012 | Conversion of portion of existing SFD to ADU | 1 | Yes | TRPA-ALLOC-2119 | Yes - Achievable | Acknowledged, Not Completed | 2022-12-14 | Residential Dwelling | Carson Philip/Jay Kniep | Carson Philip? | Conversion of portion of existing SFD to ADU. |  |  |  |  | Brandy | ADU | South Lake Tahoe | Acknowledged 4/19/2023 Conditional Permit 2/6/2023 | DR |  | 2.75 | 81
ERSP2021-0983 | Withdrawn | Withdrawn | 083-201-001 | ADU Addition | 0 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | 2021-06-29
PREC2021-1709 | Withdrawn | Withdrawn | 083-085-014 | Owner wants to convert existing accessory living space to ADU. Need SFD application | 0 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | 2021-12-03
ERSP2021-0155 | Withdrawn | Withdrawn | 094-174-005 | Withdrawn | 0 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | 2021-03-01 | Residential Dwelling | Eric Shephard | Thomas and Heidi Spirgi | Build new ADU over new Garage | E |  |  | 44295 | Karen | On hold, waiting to find development right, although TRPA issued temporary Bonus Unit, they may not take it. They may rent it out but they just don't know and really don't want to be tied to the Bonus Unit requirements. Husband has an accent, wife doesn't. 8/30/2022. Told them to contact Emily Setzer to see if they may be finding a way to give away development rights. | Placer | Withdrawn 6/27/2023 Conditional Permit 6/18/2021 | MR |  |  |  |  | 3 | Too expensive to get Development right and to build ($800/sf!) Going with a pre-fab design. Check in with them later - maybe a Best in Basin? Last communicated with them on this plan on 10/6/2022.
ERSP2021-1885 | Withdrawn | Withdrawn | 015-032-008 | Withdrawn | 0 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | 2021-11-30 | Residential Dwelling | Hayden | Hayden | New SF with ADU | E |  |  |  | Karen |  | El Dorado | Withdrawn | DR | n/a | n/a
ERSP2022-0238 | Withdrawn | Withdrawn | 116-210-078 | Withdrawn | 0 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | 2022-03-04 | Residential Dwelling | Schwiesow | PADILLA ALEJO T & DIPRINZIO SARAH M | remodel and ADU - SAHARA ST | e - Bryn | 3/14/22 bmm | Bryn | 3/21/22 bmm | Karen |  | Placer County | Withdrawn Conditional Permit 5/11/2022 | DR |  | 2.25 | 67
ERSP2023-1390 | Additional Information | Additional Information | 125-161-43 | Add a 2-car garage with living above. Not an ADU. | 0 | TBD | TBD | TBD | Not Issued, Additional Info required | 2023-09-21
ERSP2020-2100 | Incomplete Submittal | Incomplete Submittal | 115-020-041 | Proposed ADU, Request deed-restricted unit | TBD | TBD | TBD | TBD | Not Issued, Incomplete application | 2020-12-18 | Residential Dwelling | Lokwing Jare | Lokwing Jare | ADU, Cottage, granny flat 749 SF floor area, plus 558 SF garage and garage storage | E | 44257 | Karen |  | Karen | Has not responded to incomplete letter. Missing Historic Determination, BMPs, clear plans | Placer | Incomplete |  |  |  |  | 6 applications | 1 | Acknowledged
ERSP2021-0677 | Hold For Applicant | Hold for Applicant | 092-190-034 | Conversion of second floor storage space in garage into an ADU, Request deed-restricted unit | TBD | TBD | TBD | TBD | Not Issued, Applicant requested hold | 2021-05-17 | Residential Dwelling | Eric Good |  | Old Mountain ADU - convert existing space into ADU | E | 44397 |  |  | Karen | Waiting for information about whether they will do development right or Bonus Unit | Placer | On hold for applicant | MR |  |  |  |  | 1 | Assigned
ERSP2021-1409 | Incomplete Submittal | Incomplete Submittal | 083-350-004 | Convert second story of detached garage into ADU, Request deed-restricted unit | TBD | TBD | TBD | TBD | Not Issued, Incomplete application | 2021-09-14 | Residential Dwelling | Jessica Taff | Kilmer | Convert second story of detached garage into ADU with no change to coverage. Want to deed-restrict. | E | 44456 | Karen |  | Karen | Missing BMPs, Site Assessment | Placer | Incomplete | DR
ERSP2021-1965 | Incomplete Submittal | Incomplete Submittal | 093-152-003 | Basement conversion into a ADU, Request deed-restricted unit | TBD | TBD | TBD | TBD | Not Issued, Incomplete application | 2021-12-22 | Residential Dwelling |  | Frappia | Turn basement into ADU on Panorama in Tahoe City | E |  |  |  |  | Linda saw this, it's not yet assigned | Placer County | Incomplete | MR
ERSP2022-1459 | Incomplete Submittal | Incomplete Submittal | 117-120-038 | Residential Dwelling single story granny unit | TBD | TBD | TBD | TBD | Not Issued, Incomplete application | 2022-08-01 | Residential Dwelling | Billings | BILLINGS NOELL & BILLINGS MICHAEL & Katherine Billings |  | e-TLS | 44791 | TLS |  | Intake | See Record info | Placer County | Incomplete | Don't know
ERSP2022-1518 | Incomplete Submittal | Incomplete Submittal | 1318-24-311-015 | New correct file: ERSP2021-0189-01, see below | TBD | TBD | TBD | TBD | Not Issued, Incomplete application | 2022-08-11
ERSP2023-0431 | Incomplete Submittal | Incomplete Submittal | 125-185-10 | Construct new 2 story living & extend garage area to existing residence, ADU | TBD | TBD | TBD | TBD | Not Issued, Incomplete application | 2023-04-27
ERSP2023-0624 | Incomplete Submittal | Incomplete Submittal | 029-341-001 | One duplex, One single family dwelling and One detached ADU. | TBD | TBD | TBD | TBD | Not Issued, Incomplete application | 2023-05-25
ERSP2023-0648 | Incomplete Submittal | Incomplete Submittal | 029-341-002 | Total 4 dwelling units are proposed on this site. 3 residential units and 1 detached ADU | TBD | TBD | TBD | TBD | Not Issued, Incomplete application | 2023-05-30
ERSP2023-0649 | Incomplete Submittal | Incomplete Submittal | 029-341-003 | Total 4 dwelling units are proposed on this site. 3 residential units and 1 detached ADU | TBD | TBD | TBD | TBD | Not Issued, Incomplete application | 2023-05-30
ERSP2023-0701 | Addl Information Received | Additional Information | 098-191-018 | Deed restricted ADU. | TBD | TBD | TBD | TBD | Not Issued, Additional Info required | 2023-06-07
ERSP2023-1017 | Incomplete Submittal | Incomplete Submittal | 092-170-033 | Converting storage space to be an ADU | TBD | TBD | TBD | TBD | Not Issued, Incomplete application | 2023-07-25
ERSP2023-1052 | Conditional Permit | Additional Information | 027-321-013 | Converting front structure into detached market-rate adu | 1 | No - Tranfer RUU |  |  | Issued, Not acknowledged | 2023-07-28
ERSP2023-1508 | In Review | Incomplete Submittal | 092-090-056 | Residential Dwelling Garage addition with living space above ADU utilizing Bonus | TBD | TBD | TBD | TBD | Not Issued, Incomplete application | 2023-10-09
ERSP2021-1514 | Acknowledged | Acknowledged | 026-122-036 | ADU above a garage | 1 | No - Using onsite RUU |  |  | Acknowledged, Not Completed | 2021-10-18 | Residential Dwelling | Maxhimer | [6 empty] | Brandy |  | City of South Lake Tahoe | Acknowledged 11/17/2021 Conditional Permit 10/18/2021 | Market-Rate | n/a | 0.5 | 21
ERSP2022-0605 | Acknowledged | Acknowledged | 027-111-004 | Permit existing, illegal ADU | 1 | No - Using onsite RUU |  |  | Existing | 2022-04-19 | Residential Dwelling | John McAlister | 1048 Herbert | Permit existing, illegal ADU to code compliance and legal status. (Unit #2) |  |  |  |  | Aly Borawski |  | South Lake Tahoe | (Complete) - City will permit 9/7/2022 On hold for additional Information -- 8/17/2022 Opened 4/19/2022 | MR - City will permit |  | 5.5 | 165
ERSP2023-0331 | Conditional Permit | Conditional Permit | 031-122-012 | market rate accessory dwelling unit (ADU) | 1 | No - Using onsite RUU |  |  | Issued, Not acknowledged | 2023-03-28 | Residential Dwelling | LUONG | WANG XIA HUA | ADU project | e-TLS | 45034 | TLS |  |  | Fire agency pre-approval | 63 | Conditional Permit 8/28/2023 | MR
ERSP2022-1846 | Conditional Permit | Conditional Permit | 032-241-019 | Residential accessory dwelling unit (ADU) in an already constructed accessory living area | 1 | No - Tranfer RUU/Converted from TAU | TRPA-CONVTRF-2150, TRPA-CONVTRF-2224 |  | Issued, Not acknowledged | 2022-10-05 | Residential Dwelling | Roberts | ROBERTS SHERI L | ADU- Adding Kitchen to existing accessory living space above garage to make ADU- proposed TAU conversion? Eligible for bonus unit. | e-TLS | 10/24/2022- sent from TLS email | TLS |  | Aly | ADU- Missing: Fire approval, Historic Det (unless garage was built later than 72), Findings | South Lake Tahoe | Conditional Permit 2/10/2023 | MR |  | 4 | 120
ERSP2023-0268 | Acknowledged | Acknowledged | 026-092-026 | Accessory dwelling unit (ADU) over a garage | 1 | No - Tranfer RUU/Converted from TAU | TRPA-CONVTRF-2151, TRPA-CONVTRF-2223 |  | Acknowledged, Not Completed | 2023-02-28 | Residential Dwelling | CLAYTON | CLAYTON STEPHANIE ANN | ADU | e-TLS |  |  | 45005 | Brandy | Change City permitted structure from Accessory Living Area to ADU. Full RUU to come from City. Submitting to City concurrently | 91 | Acknowledged 6/12/2023 Conditional Permit 4/19/2023 | MR |  | 1.5 | 51
ERSP2021-0189-01 | Acknowledged | Acknowledged | 1318-24-311-015 | Construction of two single-family dwellings on parcel using banked RUUs | 0 | No - RUU transfer |  |  | Acknowledged, Not Completed | 2022-09-08
ERSP2020-2043 | Acknowledged | Acknowledged | 083-172-009 | New ADU over garage | 1 | No - RUU transfer | TRPA-CONVTRF-1979 |  | Acknowledged, Not Completed | 2020-12-16 | Residential Dwelling | O'Brian | [6 empty] | Theresa |  | Placer | Acknowledged 6/10/22 Conditional Permit 1/24/2022 | Market-rate | n/a | 14 | 419
ERSP2021-0964 | Acknowledged | Acknowledged | 115-010-019 | the guest house, will become an accessory dwelling unit | 1 | No - RUU transfer | TRPA-TRF-1999 |  | Acknowledged, Not Completed | 2021-06-28 | Residential Dwelling | Soules | WARNOCK JOHN E TR ET AL | Remodel and additions to existing main and guest houses (ADU) plus modification of existing boat house. |  |  |  |  | Aly |  | Placer | Acknowledged 3/28/2022 Conditional Permit 3/28/2022 | MR |  | 9 | 270
ERSP2022-0015 | Conditional Permit | Conditional Permit | 083-085-014 | Make an existing unit into a ADU | 1 | No - RUU transfer | n/a |  | Existing | 2022-01-13 | Residential Dwelling |  | Jordan | Sent to WBA for outside consultant review |  |  |  |  | Aly/WBA |  | Placer | Conditional Permit 6/16/22 | MR - still needs to transfer an RUU as a condition of the permit |  | 5 | 153
ERSP2022-0160 | Acknowledged | Acknowledged | 031-093-021 | New ADU | 1 | No - RUU transfer | TRPA-CONVTRF-2014 |  | Acknowledged, Not Completed | 2022-03-02 | Residential Dwelling |  | CORCORAN RYAN D & HOLLY E | NEW ADU, ADD ONTO (E) SFR, NEW PARKING, TREE REMOVAL |  |  |  |  | Alyssa |  | City of South Lake Tahoe | Acknowledged 10/11/2022 Conditional Permit 6/3/2022 | MR |  | 3 | 90
ERSP2022-0277 | Conditional Permit | Conditional Permit | 032-162-002 | Construct detached accessory dwelling unit (ADU) over a garage | 1 | No - RUU transfer | TRPA-CONVTRF-2032 |  | Issued, Not acknowledged | 2022-03-09 | Residential Dwelling | Hoida | KALETA PAUL FREDERICK TR & VICKY ELIZABETH B TR | ADU application | e - Aly | 44639 | Aly |  | Brandy | Additional payment required | City of South Lake Tahoe | Withdrawn 12/14/2022 Conditional Permit, 4/28/22 | MR |  | 1.5 | 49
ERSP2022-0598 | Conditional Permit | Conditional Permit | 029-101-018 | New detached garage with ADU above. | 1 | No - RUU transfer | n/a |  | Issued, Not acknowledged | 2022-04-07 | Residential Dwelling | Hoida | PARINA BARBARA JOANNE SURV TR | adu above new detached garage |  |  |  |  | Brandy |  | South Lake Tahoe | Conditional Permit-11/10/2022 (was on hold for very long time waiting for applicants) | MR |  | n/a | n/a
ERSP2022-1399 | Conditional Permit | Conditional Permit | 031-181-015 | Addition of garage and 2nd story ADU | 1 | No - RUU transfer | TBD |  | Issued, Not acknowledged | 2022-07-20 | Residential Dwelling | Perlstein | GILARDI JENNIFER IRENE & DENNIS A TR | Garage and 2nd Story ADU | e-TLS | 44776 |  | 44931 | Aly | ADU | South Lake Tahoe | In Review, on hold additional information | ?
ERSP2022-1652 | Acknowledged | Acknowledged | 031-093-026 | Existing guest quarters unit B converted to ADU | 1 | No - RUU transfer | TRPA-TRF-2122 |  | Existing | 2022-08-29 | Residential Dwelling | Burwell | HAIDARI WAHEED W TR | ADU in existing guest flat | e-TLS | 44817 | TLS | 44819 | Karen |  | South Lake Tahoe | Acknowledged Permit 3/16/2023 Conditional Permit 11/10/2022 | MR |  | 2 | 58 | 120
ERSP2022-1694 | Acknowledged | Acknowledged | 023-182-026 | New detached ADU | 1 | No - RUU transfer | TRPA-TRF-2041 |  | Acknowledged, Not Completed | 2022-09-02 | Residential Dwelling | PROVISION | PROVISION PROPERTIES LLC CA LLC | ADU above new garage | e-TLS | 44824 | TLS | 44827 | Arlo | Outsource Review Requested | City of South Lake Tahoe | Acknowledged 11/28/22 Conditional Permit-10/10/2022 | MR |  | 1.25 | 37
ERSP2022-1915 | Conditional Permit | Conditional Permit | 031-094-002 | LIVING SPACE "ADU" OVER THE GARAGE | 1 | No - RUU transfer | n/a |  | Issued, Not acknowledged | 2022-10-19 | Residential Dwelling | Shivers | TIMOTHY SHIVERS | Renovating inside second story of detached garage to include ADU | e-TLS |  |  | 44869 | Brandy | See record info | SouthLake Tahoe | Conditional Permit 1/7/2023 Opened 11/4/2022 | MR |  | 2 | 60
ERSP2022-2025 | Acknowledged | Acknowledged | 094-102-010 | Remove existing garage/office and rebuild with new ADU | 1 | No - RUU transfer | TRPA-TRF-2123 |  | Acknowledged, Not Completed | 2022-12-09 | Residential Dwelling | edwards | WISEMAN JOHN J & YAPP-MELCHER TRACY W | Remove existing garage/office and rebuild new ADU. PRU will be transferred concurrently. | e-TLS |  |  | 44922 | Brandy | ADU | Placer County | Acknowledged 5/22/2023 Conditional Permit 2/6/2023 | MR |  | 2 | 57
ERSP2022-2030 | Acknowledged | Acknowledged | 027-233-034 | Residential Dwelling--Tear down and rebuild new MFRUU. Residence with attached ADU and 1 detached ADU | 1 | No - RUU transfer | TRPA-CONVTRF-2290 |  | Acknowledged, Not Completed | 2022-12-15 | Residential Dwelling | JABLONSKI | JABLONSKI KEVIN P & KOPJO JABLONSKI KIMBERLY TR | Tear down and rebuild new MFRUU. Residence with attached ADU and 1 detached ADU | e-TLS |  |  | 44930 | Theresa | ADU- see description | South Lake Tahoe | In Review, on hold additional information | MR
ERSP2023-0339 | Acknowledged | Acknowledged | 027-234-005 | Create a full attached ADU in the living space above the garage | 1 | No - RUU transfer | TRPA-CONVTRF-2289 |  | Acknowledged, Not Completed | 2023-04-03
ERSP2022-1999 | Conditional Permit | Conditional Permit | 032-151-009 | Tear down of an existing single-family dwelling and construction of five duplexes and two accessory dwelling units, for a total of 12 new residential units | 2 | No - RUU transfer | TRPA-CONVTRF-2334/ERSP2023-1091 |  | Issued, Not acknowledged | 2022-12-06 | Residential Dwelling | Basin Strategies Planning |  | 10 MF + 2 ADUs = 12 units |  |  |  |  | Brandy | MF/ADUs | South Lake Tahoe | Conditional Permit 3/2/2023 | 2 MR ADUs |  | 3 | 90
ERSP2022-1141 | Conditional Permit | Conditional Permit | 129-301-07 | The additional living space above the garage shall not act as a second residential unit of use (RUU). | 0 | No |  |  | Issued, Not acknowledged | 2022-06-07
ERSP2022-1557 | Acknowledged | Acknowledged | 084-182-002 | Demolition of the existing residence and guest house the construction of a new main residence, in addition to a detached secondary residence, a residential accessory structure and a gate house at the entry | 0 | No |  |  | Acknowledged, Not Completed | 2022-08-16
ERSP2022-1565 | Incomplete Submittal | Incomplete Submittal | 084-182-003 | Demolition of the existing residence and guest house the construction of a new main residence, in addition to a detached secondary residence, a residential accessory structure and a gate house at the entry | 0 | No |  |  | Not Issued, Incomplete application | 2022-08-16
ERSP2022-1837 | Acknowledged | Acknowledged | 1418-03-301-011 | Unit shall not be used in a fashion as to constitute a secondary residence or separate residential unit. This space is not permitted to contain cooking facil | 0 | No |  |  | Acknowledged, Not Completed | 2022-10-04
ERSP2023-0316 | Conditional Permit | Conditional Permit | 122-191-14 | Construction of an accessory residential structure to include a multipurpose room, shop, bathroom and patio areas. The detached structure shall not act as a second residential unit | 0 | No |  |  | Issued, Not acknowledged | 2023-03-17
ERSP2022-1042 | Acknowledged | Acknowledged | 085-250-008 | Construction of a two-bedroom guest house | 1 | No | TRPA-TRF-813 |  | Acknowledged, Not Completed | 2022-06-03 | Residential Dwelling | Ogilvy | 4250 Lake Blvd, Homewood | [5 empty] | Aly Borawski | This is called a "Secondary Unit." Not sure if it has a kitchen - wait and see if it used a development right when it's complete. For now assume yes. | Placer | Acknowledged-9/7/2022 Conditional Permit 8/31/2022 | MR, used an allocation |  | 3.5 | 101
ERSP2023-1727 | In Review | Received | 090-115-037 | New detached ADU | TBD | TBD | TBD | TBD | Not Issued, In Review | 2023-11-30
ERSP2023-1513
ERSP2023-0429
ERSP2024-0039
TRP23-90043 |  |  | 094-231-007 | TRPA PROJECT Remodel to the interior and exterior of the existing home on deck as well as addition of 100 sf of living space. New detached garage and ADU with 636 sf of living space and 738 sf of non living. new 820 sf pervious paver driveway | [5 empty] | 2023-05-12 | Residential Addition > 3000
TRP23-90154 |  |  | 117-090-068 | TRPA ADU @ TRPA The proposed project includes the conversion of existing unconditioned storage area above garage to an accessory dwelling unit. Storage/ garage to living space---------612sf Gas Schematic Deferred | [5 empty] | 2023-11-02 | Residential Addition > 3000
TRP24-90002 |  |  | 092-031-024 | TRPA Project @ MOU THE SCOPE OF THIS PROJECT INCLUDES ADDING A NEW 1,039 SFT GARAGE WITH A 806 SFT ACCESSORY DWELLING UNIT (ADU) ABOVE THE GARAGE. THE ADDITION WILL BE MADE TO AN EXISTING DEVELOPED LOT. SITE BEST MANAGEMENT PRACTICE'S (BMP'S) AS REQUIRED BY THE TAHOE REGIONAL PLANNING ASSOCIATION (TRPA) WILL BE ADDED AS WELL. Deferred: Solar PLN23-00083, Approved 12/14/2023: Subdivision Map Modification to reduce the mapped 20-foot front setback to 12 feet (11 feet to eaves). | [5 empty] | 2024-01-02 | Residential Addition > 3000
TRP20-90029 |  |  | 117-072-005 | TRPA @ TRPA Convert Guest House to ADU(kitchen addition) Planning approved; PLN19-00368 Minor Use Permit Final on Guest House permit #531801; sm | [5 empty] | 2020-04-06 | Secondary Dwelling
TRP19-90267 |  |  | 085-081-024 | TRPA @ TRPA per HB 7/2/2020 due to ADU/secondary dwelling. sm ***SHORT SUBMITTAL*** New SFD *Living Area: 1,931 sf *Deck: 240 sf *Porch: 45 sf *Please confirm with ESD if grading permit is needed, and driveway easement issue. Special inspection required shear nailing 4" and less soils per geotechnical report trusses over 60" | [5 empty] | 2019-12-31 | Single Family > 3000
TRP21-90031 |  |  | 117-190-006 | Construction of new detached two car garage with ADU above New asphalt driveway | [5 empty] | 2021-02-24 | Garage Accessory Living
TRP21-90051 |  |  | 083-201-001 | Outsourced Plan review to CSG TRPA REVIEW AT TRPA Detached ADU Living Space-------------640SF Storage------------------- 320SF Deck and Balcony------230SF Entry Porch and Stairs- 64SF Special lnspection Required | [5 empty] | 2021-03-17 | Garage Accessory Living
TRP22-90037 |  |  | 093-310-029 | THE PROJECT IS TO ADD A (N) ADU W/ 2 BEDROOMS, 2 FULL BATH, LAUNDRY SPACE, KIT./ DINING AND LIVING RM. LIVING - 954 S.F. DECK - 72 S.F. | [5 empty] | 2022-02-01 | Accessory Dwelling Unit
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Permit not in Accela - requested copy from Alyssa